## Sheet1
Overview
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Task summary | Introduction to Prototyping | Refer to Prototype_2.pdf | Refer to Prototype_3.pdf | Refer to Week 3 Protocol Feedback - Need a prototype and updated diagrams on submodule level | Refer to Prototype_4.pdf | Refer to Prototype_4.pdf | Working on feedback from colloquium | Refer to Prototype_05.pdf | Refer to Prototype_05.pdf | Refer to Prototyping_06_finalSubmission.pdf
Protocol / Discussion |  | 1. Concretize the rescue robot use case - Specify the concrete scenario your group like to consider Ans) Mountainous areas, river side eg) Lippe river, Rhine river 2. Analyse the system context - Who are the stakeholders? Ans) Government officials - Which reglementations have an influence on your system? Ans) Ask professors for more information The standards needed for approval of use - Which interface does your system has to the environment? Ans) Ultrasound sensor - to check the depth of the river Infrared camera - to check human or any hindrance around Siren alarm - to alert people around - What is the concrete boundary? Ans) Any object that is on land Just river or somewhat smaller than river's size 3. Use as documentation the possibilities of SysML and UML | 1. Refine your diagrams with respect to the feedback - Furthermore, refine the environmental model including the application of parametric diagrams (see Systems Engineering lecture) - Consider the situation that the to be rescued object sends audio and / or light information that you should be able to detect and follow - What impact do these factors have on your design draft? Which parameters have to be considered? - See slide 4 of the possible environmental elements - Refine your system and define subsystems. - Refine your design idea - As a prototype and / or a sketch / models etc. – something to talk about - No prototype no meeting! | Discussion on working on the sub-system level tasks - Requirements diagram and function Diagram to be done by Olaniyi Alao - Behaviour Diagram(sequence diagram) and Activity Structure(Activity Diagram) to be done by Heansuh Lee - Shape(updated Design) by Yigitcan Aydin - System of Objectives and Environment diagram (parametric diagram) to be done by Syed Rafsan Eham Next meeting about the progress so far on Tuesday 19th May, 2020 at 8am | Refer to Prototype_4.pdf | Colloquium -Meeting on Sunday 31st May 2020, at 19:00 in attendance was Lee & Alao -We discussed on the progress so far about the tasks that where shared. -Lee talked about the fact that he will be working on the design improvements because was done with the electronic circuit He will improve the design to implement the correction Professor Neuburg made. -Alao talked about the activity diagrams and software implementations he has done so far The remaining tasks he will be working on are the code implementation of obstacle detecting and obstacle avoidance wth their respective activity diagram. The meeting was adjourned until Tuesday 2nd of June to present the overall final solution and prepare slides for the Colloquium. -Meeting on Tuesday 2nd June 2020, at 19:00; everyone attended -Discussed about how colloquium should be carried out, and briefing on previous meeting for those who could not attend -Lee discussed about design parts and showed everyone how he will carry out the slides for the colloquium -Eham is in charge of circuit elements / diagrams, and he is working on the slides -Alao told the rest of us about the progress so far and he will present UML and code -Yigit will do slides based on user interface and he will be working on the slide There will be a final meeting on Thursday before the colloquium together for rehearsal | Hardware elements -Meeting on 8 June 2020, Monday, at 19:00; everyone attended -Discussed about System Engineering lecture's contents for our group's next plan -Need to make use of MATLAB or Python for bonus points; individual work -Lee will be in charge of design and continue making it for 3D design -Eham will be in charge of code and implementation of it for one algorithm -Alao will be in charge of code and implementation of it for one algorithm -Yigit will be in charge of circuit simulation Another meeting on Thursday | We discussed about the progress made so far with the new tasks. Alao talked about using cpp for the implementation of the overall algorithm and simulating some of the parts in tinkercad. Lee talked about continuing with the design and also implementing ultrasonic sensors in the front and back of the vehicle as well as loudspeaker on-top and water sensor beneath Syed and Aydin were not in attendance (due to work). The next meeting is on Sunday --> postponed to Monday due to work -Meeting on 15 June 2020, Monday, at 19:00; everyone attended (Syed left halfway) -Discussed about our current progress -Lee will be finishing the design part by adding door handles to the car body -Alao is almost done with codes; he will finish it by editing some parts of them (i.e. ultrasonic sensors, only two - one at the front and at the back) -Yigit will be in charge of circuit simulation | 6/21/2020 - We created another powerpoint presentation for submission to the professor. -We discussed on what parts of the projects we will be talking about. In attendance was Lee and Alao. | 08/07/2020 - We worked on final paper submission via Overleaf. - We divided the parts into many different sections. - There was no meeting for this final paper submission.
Alao Olaniyi |  | Paper model created | In-charge of function diagram Could not attend | Attended | Attended | UML, coding | Code | Code | - | -
Yigitcan Aydin |  | Idea generation on 3D model - tank-like boat, military style | Requirement diagram, use case diagram (application scenarios) | Attended | Attended | Design, coding | Circuit simulation | Circuit simulation | - | -
Heansuh Lee |  | Block body diagram and internal body diagram created | Activity diagram for behavioural diagram | Attended | Attended | Electronic circuit sensors, design | Design | Design | - | -
Syed Rafsan Ishatique |  | Idea brainstorming on 3D model - amphibious vehicle | Environment Diagram | Attended | Attended | Coding, electrical circuit | Code | - | - | -